## Project budget
Project Hermes — AI support assistant. Development and rollout budget
Version of 25.06.2026 — draft, estimates from the tech lead and vendors, not final
Item | Amount, $ | Comment | Source / owner
TEAM (4 months)
PM (0.4 FTE × 4 mo) | 4000 | Project management, client communication | Tech lead
ML/LLM engineer (1.0 × 4 mo) | 11500 | Assistant core, RAG, prompting, eval | Tech lead
Backend developer (0.7 × 4 mo) | 7000 | Helpdesk integration, API, queues | Tech lead
ML data engineer (0.4 × 4 mo) | 3000 | Knowledge-base collection and preparation | Tech lead
QA engineer (0.4 × 4 mo) | 2500 | Test cases, acceptance set, regression | Tech lead
TOTAL team
INFRASTRUCTURE AND LICENCES
Inference / LLM API (development + test) | 1800 | Per the chosen vendor (ModelAPI) | Inference vendor
Cloud (dev / stage) | 1000 | Development and test environments | Cloud provider
Vector DB / embedding store | 700 | Knowledge-base storage | VectoDB
Tooling (monitoring, CI/CD) | 450 | Logs, alerting, builds | —
TOTAL infrastructure
DATA AND CONTENT
Knowledge-base prep/labelling (contractor) | 2000 | Policies, FAQ, tariffs into RAG | Labelling contractor
Data collection and cleaning | 1000 | Exports from Hermes systems | Internal
TOTAL data
OTHER
Assistant UI design | 900 | UI for operator suggestions | Designer
Legal support (contract, NDA, GDPR) | 700 | Contract and personal-data review | Law firm
Pilot / trial operation | 1000 | 2-week pilot with a subset of operators | Internal
Risk reserve (10%) |  | Formula: 10% of the sum above | —
TOTAL other
PROJECT TOTAL COST
Contract value | 69000 | Gross margin ≈ 40% — below the 45% target per PS-01, needs review

## Monthly (support)
Forecast monthly support costs (after go-live in production)
Attention: verify the client's SLA rate ($4,200/month) against the contract
Item | Amount, $/mo | Comment
Inference / LLM API (prod) | 1050 | ModelAPI, ~ production traffic volume
Cloud / infra (prod) | 420 | Production environment
Vector DB / storage | 180 | VectoDB
Monitoring and alerting | 120 | Logs, quality dashboards
Support (engineer, part-time) | 780 | Incidents, fine-tuning, knowledge-base updates
TOTAL monthly
For reference: client SLA payment $4,200/month → support is profitable.