# What we want from the AI support assistant (draft spec, raw)

Jotted down between calls with Hermes, we’ll comb it through and write it up properly later. — PM

So, the task is this. Hermes (Hermes Logistics Ltd, 3PL, warehouses and freight, nationwide) has support drowning. They want an AI assistant that sits on top of their knowledge base — policies, tariffs, shipment statuses, FAQ — and helps the operators answer. It should also close some of the requests itself, without pulling in a human. This is LLM+RAG, not a button chat-bot, spell that out to them straight away or they’ll be expecting “little buttons”.

The main goal in the client’s own words (Paul Denton, director of client service, also the decision-maker): “so the client gets one and the same correct answer, whichever operator picks the request up, and gets it fast”. Irene Vance (ops director) adds — there’s no one to answer at night, the assistant has to cover the gap on the night shifts. Those are the two main “why”s, and we dance from them.

What it has to be able to do (all jumbled, as dictated):

- prompt the operator with an answer right in their helpdesk, the operator sees the hint and either sends it or edits it

- close some routine questions completely on its own (shipment status, tariffs, “where’s my truck”, warehouse opening hours etc.)

- MUST give a reference to the policy/clause it took the answer from. On the pilot, answers “out of thin air” drove people mad, no one believes it without a source

- no making things up. If it doesn’t know — honestly “don’t know, escalating”, not inventing a tariff!! This is critical, trust rests on it

- escalate the hard stuff to a human (live operator / shift senior). What counts as “hard” still needs defining, it’s vague for now

On tone. Answer politely and formally, no waffle, no bureaucratese. Uniform wording — that’s actually one of the main pain points, right now every operator has their own answer to the same question. We’ll discuss the tone with their marketing, they seem to have a communication guide, ask for it.

Tech notes (this is ours, for the team, we’ll pull it out into a separate section in the clean spec):

- integration with their helpdesk is mandatory. Which one exactly — being clarified, at discovery we found out it’s a helpdesk + a pile of Excel exports, horror (see the discovery notes)

- RAG over the knowledge base, the base has to be collected and labelled — policies/tariffs/FAQ are scattered, lying all over the place

- vector DB for the embeddings (we budgeted VectoDB)

- inference — we picked the ModelAPI vendor, per-request, 7-day postpay. Production volumes to be estimated separately

- latency!! on the pilot it lagged at peak hours, answers took several seconds and more. Fix the target response time in the spec, or we’ll get burned again. What to set — to be discussed, maybe 2-3 sec for a hint?

- personal data / GDPR — there’s client personal data in the requests, hand it to the lawyers, it’s in the contract

Success metrics (the client loves them, and we’re the ones passing acceptance against them). Jotted down as is for now, the numbers to be agreed with them:

- answer accuracy — on Atlant it was 94% on the acceptance set, aim roughly for the same here, but get the number approved with the client

- share of requests closed by the assistant without a human — grows month on month

- response speed / latency within the norm (see above, number to be pinned down)

- reduction in request handling time for the operators

- share of hallucinations / answers without a source — tends to zero

What we are NOT doing (so the scope doesn’t drift; the warranty in the contract is vague, “not meeting expectations” is a trap, the lawyer flagged it): no telephony/voice at the start, text only (email/chat). No multi-language, English only. We’re not rewriting their helpdesk, only integrating with it. Voice and calls — maybe in the second release, separately and for money.

Timing and money for context (not for designing the spec, but to keep the frame in mind): contract $69,000, go-live in production by 01.10.2026, 4 months from the advance payment. Support after launch under an SLA at $4,200/month. Stages: discovery and data → development → rollout and acceptance.

What else needs closing to make the spec proper (note to self, don’t forget):

- define clearly what a “hard request” is and the escalation rules

- pin the target latency down to a number

- agree the acceptance metrics with the client (especially accuracy %)

- get their tone/communication guide from them

- find out exactly what their helpdesk is and the export formats (that’s for discovery)

- list of topics/categories of questions the assistant closes itself vs hint only

They also need an avatar and a name for the assistant, but that’s for later. Denton suggested “Hermes Helper”, sounds meh, we’ll discuss. That’s it, sending as is, we’ll structure it next.